## Data
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-8834 | Normal | Unassigned | Coding Queue | New Feature | 3 | 188.75 | 0 |  | SCM - 2022.R6 05/23
WMSP-8833 | Normal | Unassigned | Coding Queue | Architectural | 2 | 258.75 | 0 |  | SCM - 2022.R6 05/23
WMSP-8683 | Normal | Unassigned | Coding Queue | New Feature | 5 | 288.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8681 | Normal | Unassigned | Coding Queue | New Feature | 2 | 288.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8674 | Normal | Unassigned | Coding Queue | New Feature | 3 | 288.75 | 5 |  | SCM - 2022.R6 05/23
WMSP-8673 | Normal | Orkun Dokmen | Coding Queue | New Feature | 3 | 288.75 | 8 |  | SCM - 2022.R6 05/23
WMSP-8644 | High | Orkun Dokmen | Coding | New Feature | 1 | 301.25 | 1 |  | SCM - 2022.R6 05/23
WMSP-8616 | Normal | Unassigned | Coding Queue | Architectural | 8 | 238.75 | 0 |  | SCM - 2022.R6 05/23
WMSP-8599 | High | Unassigned | Coding Queue | Defect | 3 | 301.25 | 3 |  | SCM - 2022.R6 05/23
WMSP-8594 | Normal | Unassigned | Coding Queue | New Feature | 3 | 188.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8574 | High | Nazli Saka Aydin | Coding | New Feature | 3 | 301.25 | 3 |  | SCM - 2022.R6 05/23
WMSP-8573 | Normal | Unassigned | Coding Queue | New Feature | 3 | 208.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8549 | Normal | Unassigned | Coding Queue | Defect | 3 | 188.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8542 | Normal | Ali Celik | Coding | New Feature | 3 | 208.75 | 2 |  | SCM - 2022.R6 05/23
WMSP-8499 | High | Unassigned | Coding Queue | New Feature | 8 | 238.75 | 3 |  | SCM - 2022.R6 05/23
WMSP-8473 | High | Unassigned | Coding Queue | Defect | 3 | 301.25 | 8 |  | SCM - 2022.R6 05/23
WMSP-8206 | Normal | Unassigned | External Dependency | Defect | 0 | 288.75 | 8 |  | SCM - 2022.R6 05/23
WMSP-7958 | Normal | Arda Horozlu | Request - Paused | Architectural | 8 | 238.75 | 13 | 2 | SCM - 2022.R5 04/18, SCM - 2022.R6 05/23
WMSP-7328 | Normal | Nazli Saka Aydin | Coding Review Queue | New Feature | 3 | 223.75 | 8 |  | SCM - 2022.R6 05/23

## Sheet2
WMSP-8681 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-7328 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 8]
WMSP-8499 | [Story | Points | (Coding), | Story | Points | (Test)] | [8, | 3]
WMSP-8206 | [Story | Points | (Coding), | Story | Points | (Test)] | [0, | 8]
WMSP-8834 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 0]
WMSP-8574 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-8594 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-8674 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 8]
WMSP-7958 | [Story | Points | (Coding), | Story | Points | (Test)] | [8, | 13]
WMSP-8599 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-8833 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 0]
WMSP-8683 | [Story | Points | (Coding), | Story | Points | (Test)] | [8, | 3]
WMSP-8549 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-8644 | [Story | Points | (Coding), | Story | Points | (Test)] | [1, | 1]
WMSP-8573 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]
WMSP-8673 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 8]
WMSP-8616 | [Story | Points | (Coding), | Story | Points | (Test)] | [8, | 0]
WMSP-8473 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 8]
WMSP-8542 | [Story | Points | (Coding), | Story | Points | (Test)] | [3, | 3]

## PropertyDefinitions
Özellik Adı | Değer | Açıklama
Request Type | Defect | Defect
Request Type | New Feature | New Feature
Request Type | Architectural | New Feature
Priority | Normal | Normal
Priority | High | High
Priority | Urgent | High
Priority | Low | Low
Priority | Lowest | Low
Business Value | 288.75 | 300
Business Value | 238.75 | 200
Business Value | 0 | 0
Business Value | 316.25 | 300
Business Value | 301.25 | 300
Business Value | 223.75 | 200
Business Value | 108.75 | 100
Business Value | 348.75 | 300
Business Value | 218.75 | 200
Business Value | 405 | 400
Business Value | 183.75 | 200
Business Value | 208.75 | 200
Business Value | 173.75 | 200
Business Value | 353.75 | 300
Business Value | 313.75 | 300
Business Value | 158.75 | 100
Business Value | 138.75 | 100
Business Value | 103.75 | 100
Business Value | 188.75 | 200
Business Value | 258.75 | 200
Story Points (Test) | 0 | 0
Story Points (Test) | 1 | 1
Story Points (Test) | 2 | 3
Story Points (Test) | 3 | 3
Story Points (Test) | 5 | 8
Story Points (Test) | 8 | 8
Story Points (Test) | 3 | 3
Story Points (Test) | 13 | 13
Story Points (Test) | 1 | 1
Story Points (Coding) | 1 | 1
Story Points (Coding) | 2 | 3
Story Points (Coding) | 3 | 3
Story Points (Coding) | 5 | 8
Story Points (Coding) | 3 | 3
Story Points (Coding) | 8 | 8
Story Points (Coding) | 13 | 13
Story Points (Coding) | 34 | 34
Story Points (Coding) | 21 | 21
Story Points (Coding) | 0 | 0

## PropertyValueNormalization
Özellik Adı | Değer | Açıklama
Request Type | Defect | Defect
Request Type | New Feature | New Feature
Request Type | Architectural | New Feature
Priority | Normal | Normal
Priority | High | High
Priority | Urgent | High
Priority | Low | Low
Priority | Lowest | Low
Business Value | 288.75
Business Value | 238.75
Business Value | 0
Business Value | 316.25
Business Value | 301.25
Business Value | 223.75
Business Value | 108.75
Business Value | 348.75
Business Value | 218.75
Business Value | 405
Business Value | 183.75
Business Value | 208.75
Business Value | 173.75
Business Value | 353.75
Business Value | 313.75
Business Value | 158.75
Business Value | 138.75
Business Value | 103.75
Business Value | 258.75
Business Value | 188.75
Story Points (Test) | 0 | A
Story Points (Test) | 1 | B
Story Points (Test) | 2 | C
Story Points (Test) | 3 | C
Story Points (Test) | 5 | D
Story Points (Test) | 8 | D
Story Points (Test) | 3 | C
Story Points (Test) | 13 | E
Story Points (Test) | 1 | B
Story Points (Coding) | 1 | B
Story Points (Coding) | 2 | C
Story Points (Coding) | 3 | C
Story Points (Coding) | 5 | D
Story Points (Coding) | 3 | C
Story Points (Coding) | 8 | D
Story Points (Coding) | 13 | E
Story Points (Coding) | 34 | G
Story Points (Coding) | 21 | F
Story Points (Coding) | 0 | A

## Sheet1
# | Selected Issue Type | key | sp | week | cw | status | assg | 81 | 27
1 | New Feature.Normal.200.3.3 | WMSP-8176 | 3 | 1 | 1 | Coding | Orkun Dokmen |  |  |  |  | WMSP-8176
2 | Defect.High.300.3.8 | WMSP-8296 | 5 | 1 | 0 | Coding Queue | Unassigned |  | 1 | 25 | 6 | WMSP-8176,WMSP-8296
3 | New Feature.Normal.100.1.3 | WMSP-8241 | 3 | 1 | 0 | Coding Queue | Unassigned |  | 2 | 29 | 5 | WMSP-8176,WMSP-8296,WMSP-8241
5 | New Feature.Normal.0.3.3 | WMSP-8539 | 3 | 1 | 0 | Coding Queue | Unassigned |  | 3 | 27 | 5 | WMSP-8176,WMSP-8296,WMSP-8241,WMSP-8539
6 | Defect.Low.200.1.3 | WMSP-7810 | 3 | 1 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-8176,WMSP-8296,WMSP-8241,WMSP-8539,WMSP-7810
15 | New Feature.Normal.200.13.8 | WMSP-7847 | 8 | 1 | 2 | External Dependency | Ali Celik |  |  |  |  | WMSP-8176,WMSP-8296,WMSP-8241,WMSP-8539,WMSP-7810,WMSP-7847
4 | New Feature.Normal.200.13.8 | WMSP-7958 | 8 | 2 | 0 | Request - Paused | Merve Aktas |  |  |  |  | WMSP-7958
7 | New Feature.High.300.8.13 | WMSP-8488 | 13 | 2 | 0 | Analysis Queue | Serdar Caliskan |  |  |  |  | WMSP-7958,WMSP-8488
8 | New Feature.Normal.200.3.8 | WMSP-8172 | 5 | 2 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-7958,WMSP-8488,WMSP-8172
9 | New Feature.Normal.0.3.3 | WMSP-8538 | 3 | 2 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-7958,WMSP-8488,WMSP-8172,WMSP-8538
10 | Defect.High.200.3.8 | WMSP-8501 | 5 | 3 | 0 | Analysis Queue | Serdar Caliskan |  |  |  |  | WMSP-7958,WMSP-8488,WMSP-8172,WMSP-8538,WMSP-8501
11 | New Feature.Normal.100.1.3 | WMSP-7458 | 3 | 3 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-7458
12 | Defect.Normal.200.3.3 | WMSP-8471 | 3 | 3 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-7458,WMSP-8471
13 | New Feature.Normal.0.0.13 | WMSP-8543 | 13 | 3 | 0 | Coding Queue | Samil Algul |  |  |  |  | WMSP-7458,WMSP-8471,WMSP-8543
14 | New Feature.Low.100.3.3 | WMSP-7020 | 3 | 3 | 0 | Coding Queue | Unassigned |  |  |  |  | WMSP-7458,WMSP-8471,WMSP-8543,WMSP-7020
16 | Defect.High.300.0.1 | WMSP-8329 | 0 | 3 | 0 | Coding Queue | Ali Celik |  |  |  |  | WMSP-7458,WMSP-8471,WMSP-8543,WMSP-7020,WMSP-8329
81

## Data2
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-6125 | Lowest | Russell Gorczany | External Dependency | Defect | 0 | 353.75 | 3 |  | SCM - 2023.R1 04/23
WMSP-9207 | Normal | Davis Rempel | Coding Review Queue | Defect | 21 | 158.75 | 0 |  | SCM - 2023.R5 07/23
WMSP-0658 | High | Tam Morissette | Coding Queue | Architectural | 8 | 138.75 | 3 |  | SCM - 2023.R1 07/23
WMSP-1058 | Lowest | Jackson Davis | Coding Queue | Defect | 21 | 103.75 | 0 |  | SCM - 2023.R5 08/23
WMSP-7425 | Low | Daren Lehner | Coding Review Queue | Architectural | 3 | 353.75 | 0 |  | SCM - 2023.R7 08/23
WMSP-7691 | Normal | Denny Hamill | External Dependency | New Feature | 3 | 223.75 | 13 |  | SCM - 2023.R0 07/23
WMSP-5014 | Low | Thomas Raynor | Coding | Architectural | 13 | 313.75 | 3 |  | SCM - 2023.R1 06/23
WMSP-1986 | Low | Karla Renner | External Dependency | Defect | 13 | 208.75 | 2 |  | SCM - 2023.R0 09/23
WMSP-1269 | Lowest | Glynis Dare | Coding Review Queue | Defect | 13 | 188.75 | 3 |  | SCM - 2023.R8 01/23
WMSP-9911 | Urgent | Alton Anderson | Coding Queue | Architectural | 3 | 183.75 | 13 |  | SCM - 2023.R3 04/23
WMSP-4060 | Normal | Tommy Blick | Coding Review Queue | Defect | 3 | 313.75 | 1 |  | SCM - 2023.R6 09/23
WMSP-7490 | High | Robby Leuschke | Coding | New Feature | 5 | 223.75 | 1 |  | SCM - 2023.R7 07/23
WMSP-9505 | Urgent | Magen Hahn | Coding Queue | New Feature | 5 | 188.75 | 5 |  | SCM - 2023.R1 08/23
WMSP-4015 | Low | Brittaney Will | Coding Review Queue | Architectural | 3 | 183.75 | 3 | 1 | SCM - 2023.R6 05/23
WMSP-0263 | High | Chandra Frami | Request - Paused | Architectural | 3 | 173.75 | 8 |  | SCM - 2023.R8 02/23
WMSP-8834 | Low | Arnoldo Zulauf | Request - Paused | New Feature | 34 | 0 | 13 |  | SCM - 2023.R5 00/23
WMSP-7732 | High | Samuel Rau | Request - Paused | Architectural | 3 | 183.75 | 13 |  | SCM - 2023.R2 07/23
WMSP-5869 | High | Meagan Reinger | Coding Queue | Defect | 3 | 313.75 | 0 |  | SCM - 2023.R1 06/23
WMSP-9609 | Low | Taylor Nienow | Coding Review Queue | Defect | 34 | 301.25 | 8 |  | SCM - 2023.R1 02/23
WMSP-4347 | Normal | Ulysses Brakus | Coding | Architectural | 8 | 353.75 | 1 |  | SCM - 2023.R8 06/23
WMSP-3912 | Lowest | Omer Mills | Coding Review Queue | Architectural | 8 | 218.75 | 8 |  | SCM - 2023.R6 04/23
WMSP-3055 | Urgent | Jonelle Nikolaus | External Dependency | Architectural | 34 | 103.75 | 1 |  | SCM - 2023.R7 07/23
WMSP-7212 | High | Rosaria Will | Coding | New Feature | 13 | 188.75 | 3 |  | SCM - 2023.R3 02/23
WMSP-3451 | Normal | Russ Mills | Coding Queue | Defect | 13 | 353.75 | 13 |  | SCM - 2023.R2 01/23
WMSP-2712 | Lowest | Lyle Beahan | Coding Review Queue | Architectural |  | 238.75 | 0 |  | SCM - 2023.R8 07/23
WMSP-8480 | Lowest | Deshawn Ledner | Request - Paused | Defect | 2 | 183.75 | 0 |  | SCM - 2023.R2 07/23
WMSP-4177 | Low | Shala Runolfsson | External Dependency | Defect | 0 | 238.75 | 3 |  | SCM - 2023.R0 06/23
WMSP-7660 | Lowest | Ola Gutmann | External Dependency | Architectural | 0 | 301.25 | 5 |  | SCM - 2023.R0 03/23
WMSP-9816 | High | Tobi Wisoky | External Dependency | New Feature | 2 | 173.75 | 0 |  | SCM - 2023.R5 04/23
WMSP-2000 | High | Galina Kautzer | External Dependency | New Feature |  | 288.75 | 3 |  | SCM - 2023.R5 03/23
WMSP-2319 | Normal | Inger Wilkinson | Coding Queue | Architectural | 3 | 238.75 | 8 |  | SCM - 2023.R2 02/23
WMSP-3911 | Urgent | Jarod O'Hara | Coding Review Queue | Architectural | 2 | 348.75 | 3 |  | SCM - 2023.R4 00/23
WMSP-8238 | Low | Myron Weimann | Coding Review Queue | Defect | 3 | 103.75 | 3 |  | SCM - 2023.R0 04/23
WMSP-9244 | Low | Annamarie Klocko | External Dependency | Architectural | 21 | 316.25 | 3 |  | SCM - 2023.R5 09/23
WMSP-4528 | Low | Tad Hermiston | Coding Queue | New Feature | 13 | 158.75 | 5 |  | SCM - 2023.R4 03/23
WMSP-3173 | High | Ronald Ledner | Coding Queue | Architectural | 21 | 173.75 | 2 |  | SCM - 2023.R2 07/23
WMSP-7337 | Urgent | Annice Heathcote | Coding Queue | Architectural | 3 | 348.75 | 3 |  | SCM - 2023.R0 00/23
WMSP-8788 | High | Petra Collier | Coding | New Feature | 13 | 223.75 | 1 |  | SCM - 2023.R6 03/23
WMSP-0784 | Lowest | Leonel Mohr | Coding | Defect | 34 | 405 | 1 |  | SCM - 2023.R3 07/23
WMSP-7024 | Lowest | Yadira Grady | Request - Paused | Defect | 5 | 208.75 | 0 |  | SCM - 2023.R5 04/23
WMSP-7435 | Normal | China Dicki | Coding Queue | Architectural | 21 | 173.75 | 2 |  | SCM - 2023.R5 07/23
WMSP-8378 | Normal | Odis Nader | Request - Paused | New Feature | 3 | 288.75 | 3 |  | SCM - 2023.R1 08/23
WMSP-3286 | Urgent | Brooke Waelchi | External Dependency | New Feature | 0 | 288.75 | 8 |  | SCM - 2023.R5 02/23
WMSP-7108 | Lowest | Olimpia Waters | Coding Queue | Defect | 5 | 208.75 | 3 |  | SCM - 2023.R0 07/23
WMSP-0292 | Low | Domingo Adams | Request - Paused | New Feature | 0 | 238.75 | 3 |  | SCM - 2023.R6 01/23
WMSP-8161 | High | Khadijah Wilderman | Coding Review Queue | New Feature | 21 | 218.75 | 8 |  | SCM - 2023.R7 01/23
WMSP-6823 | Lowest | Herschel Kozey | External Dependency | Architectural | 8 | 188.75 | 8 |  | SCM - 2023.R4 09/23
WMSP-9337 | Low | Delorse Abshire | Coding | New Feature | 5 | 288.75 | 8 |  | SCM - 2023.R4 06/23
WMSP-5465 | Low | Aundrea Littel | Coding | Defect | 34 | 173.75 | 5 |  | SCM - 2023.R6 00/23
WMSP-2927 | High | Ria Wyman | Request - Paused | New Feature | 34 | 188.75 | 0 |  | SCM - 2023.R9 06/23
WMSP-5607 | Low | Freddie Hirthe | Coding Review Queue | Defect | 0 | 238.75 | 2 |  | SCM - 2023.R9 06/23
WMSP-9575 | High | Shanti Beahan | Coding Queue | New Feature | 1 | 238.75 | 3 |  | SCM - 2023.R6 09/23
WMSP-3706 | Low | Lanny Lubowitz | Coding | Architectural | 13 | 218.75 | 8 |  | SCM - 2023.R3 02/23
WMSP-9640 | Urgent | Sherly Monahan | Coding Queue | Defect | 3 | 218.75 | 1 |  | SCM - 2023.R7 03/23
WMSP-1932 | Lowest | Earnest Beatty | Coding Review Queue | Defect | 3 | 173.75 | 1 |  | SCM - 2023.R4 02/23
WMSP-3279 | Lowest | Genie Grady | Request - Paused | Architectural | 3 | 316.25 | 3 |  | SCM - 2023.R7 00/23
WMSP-6824 | Lowest | Robt Johnson | External Dependency | Architectural | 13 | 223.75 | 13 |  | SCM - 2023.R6 01/23
WMSP-5464 | Lowest | Madge Stiedemann | External Dependency | Architectural | 3 | 218.75 | 3 |  | SCM - 2023.R2 00/23
WMSP-5600 | High | Long Herman | Request - Paused | New Feature | 5 | 348.75 | 8 |  | SCM - 2023.R5 04/23
WMSP-2811 | Low | Emma Pfeffer | Request - Paused | Architectural | 34 | 173.75 | 3 |  | SCM - 2023.R5 02/23
WMSP-3164 | Urgent | Will Maggio | Coding Review Queue | New Feature |  | 103.75 | 3 |  | SCM - 2023.R2 05/23
WMSP-5503 | Normal | Howard Bayer | External Dependency | Defect | 5 | 313.75 | 8 |  | SCM - 2023.R3 06/23
WMSP-3317 | Low | Thresa Pouros | Coding Review Queue | New Feature | 34 | 208.75 | 0 |  | SCM - 2023.R2 00/23
WMSP-3553 | Urgent | Margarito Dare | Request - Paused | New Feature | 8 | 138.75 | 1 |  | SCM - 2023.R6 03/23
WMSP-7341 | Normal | Wilbur Volkman | Request - Paused | New Feature | 3 | 108.75 | 13 |  | SCM - 2023.R2 06/23
WMSP-6388 | Normal | Beatris Ratke | Coding Queue | New Feature | 13 | 138.75 | 3 |  | SCM - 2023.R2 01/23
WMSP-1110 | Lowest | Ofelia Rutherford | Coding Queue | Architectural | 3 | 353.75 | 5 |  | SCM - 2023.R5 07/23
WMSP-1471 | Normal | Annie Sporer | Coding Queue | Defect | 5 | 138.75 | 3 | 0 | SCM - 2023.R3 01/23
WMSP-1657 | High | Tasia Heidenreich | Coding Review Queue | Defect | 3 | 0 | 1 |  | SCM - 2023.R9 07/23
WMSP-5049 | Lowest | Johnny Stoltenberg | External Dependency | Architectural | 0 | 183.75 | 2 |  | SCM - 2023.R3 09/23
WMSP-4536 | Low | Nick Greenholt | Coding Review Queue | Architectural | 0 | 405 | 3 |  | SCM - 2023.R3 03/23
WMSP-1752 | High | Ming Gutmann | Request - Paused | Architectural | 1 | 313.75 | 3 |  | SCM - 2023.R2 00/23
WMSP-5075 | Low | Austin Eichmann | External Dependency | Architectural | 8 | 138.75 | 8 |  | SCM - 2023.R6 06/23
WMSP-2961 | Urgent | Ray Turner | External Dependency | New Feature | 0 | 188.75 | 3 |  | SCM - 2023.R2 08/23
WMSP-4509 | Normal | Terese Herzog | Coding Queue | Architectural | 0 | 138.75 | 5 |  | SCM - 2023.R6 03/23
WMSP-8750 | Lowest | Dominique Larkin | Coding Queue | Architectural | 1 | 173.75 | 13 |  | SCM - 2023.R4 04/23
WMSP-3002 | Normal | Pasquale Blanda | Coding Review Queue | New Feature | 21 | 238.75 | 8 |  | SCM - 2023.R5 05/23
WMSP-1386 | Low | Perry Bailey | Coding Review Queue | Defect | 5 | 238.75 | 1 |  | SCM - 2023.R1 04/23
WMSP-0525 | Urgent | Otto D'Amore | Request - Paused | New Feature | 21 | 183.75 | 13 |  | SCM - 2023.R9 02/23
WMSP-8140 | Normal | Darci Cole | Request - Paused | Architectural | 0 | 348.75 | 13 |  | SCM - 2023.R7 09/23
WMSP-1300 | Normal | Mitchel Klein | Coding Queue | Architectural | 13 | 188.75 | 8 |  | SCM - 2023.R2 03/23
WMSP-8192 | Urgent | Tiesha Rodriguez | Request - Paused | New Feature |  | 405 | 0 |  | SCM - 2023.R9 05/23
WMSP-6579 | High | Dane Ortiz | Coding | New Feature | 21 | 288.75 | 1 |  | SCM - 2023.R7 01/23
WMSP-3440 | High | Filomena Schumm | Coding Queue | New Feature | 0 | 138.75 | 0 |  | SCM - 2023.R2 03/23
WMSP-8337 | High | Ian Stiedemann | Request - Paused | New Feature | 34 | 158.75 | 3 |  | SCM - 2023.R9 05/23
WMSP-8111 | Normal | Chantel Shanahan | Request - Paused | Defect | 3 | 188.75 | 2 |  | SCM - 2023.R1 09/23
WMSP-6073 | Normal | Irving Mertz | Request - Paused | Defect | 3 | 0 | 0 |  | SCM - 2023.R1 01/23
WMSP-3541 | Normal | Tim Dickinson | Coding | Architectural | 2 | 173.75 | 0 |  | SCM - 2023.R8 07/23
WMSP-7556 | Urgent | Morris Schmitt | External Dependency | Architectural | 34 | 183.75 | 3 |  | SCM - 2023.R8 02/23
WMSP-2780 | Low | Nisha Johnson | Coding Queue | Architectural | 1 | 313.75 | 2 |  | SCM - 2023.R9 01/23
WMSP-4938 | High | Birgit Corkery | Request - Paused | Defect | 34 | 405 | 2 |  | SCM - 2023.R3 03/23
WMSP-0238 | Normal | Chong Weimann | Coding Review Queue | Defect | 3 | 108.75 | 0 |  | SCM - 2023.R5 01/23
WMSP-9166 | High | Werner Dare | External Dependency | Architectural | 34 | 188.75 | 0 |  | SCM - 2023.R7 00/23
WMSP-8083 | Normal | Krissy Hammes | Coding Review Queue | Architectural | 8 | 0 |  |  | SCM - 2023.R8 03/23
WMSP-3564 | Normal | Kristel Feeney | External Dependency | New Feature | 0 | 218.75 | 13 |  | SCM - 2023.R9 05/23
WMSP-1006 | Lowest | Hope O'Kon | Coding | Architectural | 34 | 353.75 | 5 |  | SCM - 2023.R3 02/23
WMSP-4606 | Lowest | Mindi Cartwright | Coding | Architectural | 34 | 348.75 | 13 |  | SCM - 2023.R9 09/23
WMSP-8862 | Urgent | Noella Fisher | Coding | Architectural | 21 | 353.75 | 3 |  | SCM - 2023.R3 07/23
WMSP-8391 | Lowest | Heath Aimonetti | External Dependency | Defect | 3 | 218.75 | 3 |  | SCM - 2023.R0 05/23
| Normal | Rochell Schoen | Coding | New Feature | 5 | 405 | 2 |  | SCM - 2023.R7 01/23

## Data3
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-0089 | Urgent | Jeanne Mraz | Request - Paused | Architectural | 34 | 313.75 | 8 |  | SCM - 2023.R4 09/23
WMSP-1616 | Normal | Margy Wiza | Request - Paused | Architectural | 34 | 108.75 | 0 |  | SCM - 2023.R9 08/23
WMSP-8033 | Normal | Margarita Hilll | Coding Queue | New Feature | 2 | 223.75 | 13 |  | SCM - 2023.R3 09/23
WMSP-7088 | High | Dominique King | External Dependency | New Feature | 3 | 208.75 | 3 |  | SCM - 2023.R1 00/23
WMSP-1322 | Low | Elmo Kuhic | Coding | New Feature | 5 | 173.75 | 1 |  | SCM - 2023.R1 03/23
WMSP-8326 | Normal | Aurea Pollich | Request - Paused | Defect | 34 | 301.25 | 2 |  | SCM - 2023.R0 00/23
WMSP-8550 | Low | Claudette Kuvalis | Coding Queue | New Feature | 5 | 316.25 | 0 | 5 | SCM - 2023.R4 01/23
WMSP-0371 | Low | Jannette Watsica | Coding Review Queue | New Feature | 21 | 208.75 | 1 |  | SCM - 2023.R2 02/23
WMSP-9311 | High | Araceli Macejkovic | Coding Review Queue | Defect | 21 | 173.75 | 8 |  | SCM - 2023.R7 02/23
WMSP-8506 | Normal | Jerri Hermiston | Coding Review Queue | Architectural | 34 | 183.75 | 3 |  | SCM - 2023.R4 00/23
WMSP-6967 | Normal | Collin Kihn | Request - Paused | Defect |  | 348.75 | 8 |  | SCM - 2023.R1 07/23
WMSP-0944 | High | Norberto Crooks | Coding Review Queue | Architectural | 0 | 103.75 | 0 | 6 | SCM - 2023.R6 00/23
WMSP-7281 | Lowest | Linh Barton | External Dependency | New Feature | 21 | 405 | 5 |  | SCM - 2023.R5 08/23
WMSP-1362 | Lowest | Marcelo Christiansen | External Dependency | Defect | 2 | 316.25 | 0 |  | SCM - 2023.R8 07/23
WMSP-1882 | Urgent | Francis Cremin | Coding Queue | Defect | 21 | 208.75 | 0 |  | SCM - 2023.R4 05/23
WMSP-8253 | Urgent | Truman Roberts | External Dependency | Architectural | 8 | 313.75 | 3 |  | SCM - 2023.R4 01/23
WMSP-8780 | Normal | Flora O'Kon | Coding | Defect | 3 | 138.75 | 1 |  | SCM - 2023.R0 01/23
WMSP-5230 | High | Annette Sauer | Request - Paused | Defect | 3 | 238.75 | 1 |  | SCM - 2023.R6 00/23
WMSP-6261 | Urgent | Boyd Huel | External Dependency | Architectural | 34 | 108.75 | 1 |  | SCM - 2023.R4 07/23
WMSP-1423 | High | Octavio Osinski | External Dependency | New Feature | 1 | 158.75 | 3 |  | SCM - 2023.R9 00/23

## Data4
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-5984 | Urgent | Tomeka Lubowitz | External Dependency | Defect | 5 | 0 | 1 |  | SCM - 2023.R2 07/23
WMSP-5328 | Low | Lyndsey D'Amore | Coding Queue | Architectural | 0 | 138.75 | 5 |  | SCM - 2023.R3 09/23
WMSP-6481 | Lowest | Wesley Leffler | Coding Review Queue | New Feature |  | 238.75 | 1 |  | SCM - 2023.R3 07/23
WMSP-5764 | High | Krista Hermiston | Coding | Architectural | 0 | 218.75 | 1 |  | SCM - 2023.R9 08/23
WMSP-6060 | High | Moshe Cartwright | External Dependency | New Feature | 5 | 405 | 8 |  | SCM - 2023.R7 01/23
WMSP-2066 | Urgent | Lucien Lind | Coding Review Queue | Architectural | 5 | 108.75 | 3 |  | SCM - 2023.R4 06/23
WMSP-6116 | Lowest | Randolph Cruickshank | Request - Paused | New Feature | 5 | 138.75 | 2 |  | SCM - 2023.R7 03/23
WMSP-0685 | Urgent | Monet Collier | Coding | Defect | 5 | 348.75 | 1 |  | SCM - 2023.R3 02/23
WMSP-4261 | Lowest | Sabina Breitenberg | External Dependency | New Feature | 8 | 316.25 | 1 |  | SCM - 2023.R3 05/23
WMSP-0434 | Low | Eric Kreiger | Coding Queue | Architectural | 3 | 208.75 | 3 |  | SCM - 2023.R8 05/23
WMSP-3288 | Lowest | Willy Cormier | External Dependency | Defect | 2 | 138.75 | 3 |  | SCM - 2023.R8 08/23
WMSP-0270 | Normal | Jarrett Schuster | Request - Paused | Architectural | 2 | 0 | 1 |  | SCM - 2023.R8 03/23
WMSP-6614 | High | Suanne Kiehn | Coding Review Queue | Defect | 13 | 103.75 | 5 |  | SCM - 2023.R5 00/23
WMSP-9660 | Low | Tanna Veum | Coding Review Queue | Defect | 3 | 173.75 | 1 |  | SCM - 2023.R6 08/23
WMSP-8772 | Normal | Emory Pfeffer | External Dependency | Architectural | 3 | 183.75 | 13 |  | SCM - 2023.R2 09/23
WMSP-9715 | Normal | Travis Goodwin | Coding | Architectural | 13 | 188.75 | 1 |  | SCM - 2023.R8 04/23
WMSP-1617 | Normal | Edwardo Fahey | Coding Review Queue | Defect | 1 | 138.75 | 1 |  | SCM - 2023.R1 06/23
WMSP-4430 | High | Lawerence Stroman | Coding Queue | Architectural | 0 | 0 | 2 |  | SCM - 2023.R7 07/23
WMSP-3274 | Low | Katheleen Jacobs | Request - Paused | Architectural | 3 | 208.75 | 1 |  | SCM - 2023.R4 04/23
WMSP-3388 | Low | Vance Medhurst | Coding Review Queue | Architectural | 3 | 208.75 | 1 |  | SCM - 2023.R8 07/23

## Data5
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-6156 | Normal | Val Leannon | Coding Review Queue | New Feature | 1 | 301.25 | 0 |  | SCM - 2023.R2 04/23
WMSP-1221 | Lowest | Hobert Corwin | Coding | Defect | 2 | 348.75 | 13 |  | SCM - 2023.R7 03/23
WMSP-1075 | High | Lindy Wintheiser | Request - Paused | New Feature | 3 | 208.75 | 2 |  | SCM - 2023.R1 05/23
WMSP-7015 | Low | Neil Larkin | Request - Paused | New Feature | 5 | 223.75 | 5 |  | SCM - 2023.R6 03/23
WMSP-5473 | Normal | Camille Nikolaus | Coding | Defect | 3 | 183.75 | 1 |  | SCM - 2023.R3 03/23
WMSP-4270 | High | Mack Konopelski | Coding Review Queue | New Feature | 8 | 238.75 | 1 |  | SCM - 2023.R2 03/23
WMSP-2599 | High | Salvatore Koch | External Dependency | Defect | 13 | 173.75 | 1 |  | SCM - 2023.R7 04/23
WMSP-0215 | Low | Todd Robel | External Dependency | New Feature | 0 | 108.75 | 2 |  | SCM - 2023.R9 01/23
WMSP-2289 | High | Hobert Casper | Coding Queue | Defect | 1 | 301.25 | 13 |  | SCM - 2023.R6 06/23
WMSP-7261 | Normal | Tory Doyle | Request - Paused | New Feature | 2 | 301.25 | 0 |  | SCM - 2023.R1 02/23
WMSP-5279 | Low | Sharilyn Gottlieb | Request - Paused | Defect | 3 | 288.75 | 8 |  | SCM - 2023.R6 03/23
WMSP-8604 | Low | Andrew Fritsch | Request - Paused | Defect | 5 | 218.75 | 8 |  | SCM - 2023.R9 09/23
WMSP-5675 | Normal | Guadalupe Beer | External Dependency | Architectural | 3 | 218.75 | 3 |  | SCM - 2023.R9 04/23
WMSP-3127 | High | Waldo Beier | Request - Paused | New Feature | 8 | 183.75 | 1 |  | SCM - 2023.R4 02/23
WMSP-0442 | Urgent | Corinna Feest | Coding Review Queue | Architectural | 13 | 158.75 | 3 |  | SCM - 2023.R3 04/23
WMSP-0011 | Low | Simonne Auer | Coding | New Feature | 0 | 138.75 | 3 |  | SCM - 2023.R2 08/23
WMSP-1471 | Urgent | Napoleon Schuppe | Request - Paused | Defect | 1 | 316.25 | 2 |  | SCM - 2023.R6 06/23
WMSP-0446 | Low | Allan Dietrich | Coding Queue | New Feature |  | 301.25 | 2 | 8 | SCM - 2023.R0 02/23
WMSP-7550 | Urgent | Lyman Willms | Coding Queue | Architectural | 3 | 218.75 | 1 |  | SCM - 2023.R1 08/23
WMSP-7884 | Urgent | Jerrell Robel | External Dependency | Defect |  | 103.75 | 3 |  | SCM - 2023.R7 07/23
WMSP-5226 | Urgent | Dalton Predovic | Coding Review Queue | Architectural | 3 | 405 | 2 |  | SCM - 2023.R9 05/23
WMSP-3750 | Low | Tad Lockman | Coding | Defect | 8 | 183.75 | 5 |  | SCM - 2023.R8 01/23
WMSP-1780 | Low | Ernie Muller | Coding | New Feature | 13 | 173.75 | 3 |  | SCM - 2023.R1 08/23
WMSP-7378 | Low | Ambrose Lynch | Coding Review Queue | New Feature | 0 | 138.75 | 3 |  | SCM - 2023.R9 07/23
WMSP-7384 | Low | Bradford Koss | Coding Queue | Defect | 1 | 313.75 | 13 |  | SCM - 2023.R4 09/23

## Data6
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-4910 | Normal | Quincy Gutkowski | Request - Paused | Architectural | 1 | 316.25 | 13 |  | SCM - 2023.R3 02/23
WMSP-8926 | Normal | Quincy Brown | Coding Queue | Architectural | 2 | 316.25 | 5 |  | SCM - 2023.R1 09/23
WMSP-9694 | Urgent | Nedra Jaskolski | Coding | Architectural | 3 | 313.75 | 8 |  | SCM - 2023.R1 00/23
WMSP-7066 | Lowest | Sherilyn Boyer | Coding Review Queue | New Feature |  | 316.25 | 3 |  | SCM - 2023.R1 05/23
WMSP-4358 | High | Danita Littel | Coding | Architectural | 3 | 138.75 | 0 |  | SCM - 2023.R7 08/23
WMSP-0455 | Lowest | Geoffrey Pfeffer | Coding Review Queue | Architectural | 8 | 316.25 | 3 |  | SCM - 2023.R2 05/23
WMSP-6525 | Low | Herschel Mante | Coding | New Feature | 13 | 0 | 3 |  | SCM - 2023.R3 07/23
WMSP-3436 | Urgent | Myrtle Schuppe | Coding Review Queue | Architectural | 21 | 188.75 | 3 |  | SCM - 2023.R3 09/23
WMSP-9132 | Urgent | Katelin Stracke | Coding Review Queue | Architectural | 0 | 108.75 | 0 |  | SCM - 2023.R3 08/23
WMSP-3173 | Urgent | Vicente Bode | External Dependency | Architectural | 1 | 108.75 | 3 |  | SCM - 2023.R1 04/23
WMSP-6307 | Urgent | Trudi Hackett | Coding Queue | Architectural | 2 | 353.75 | 8 |  | SCM - 2023.R0 01/23
WMSP-9441 | Urgent | Terry Fisher | Coding Review Queue | Architectural | 3 | 158.75 | 1 |  | SCM - 2023.R7 09/23
WMSP-8390 | High | Hollis Parisian | Request - Paused | New Feature | 5 | 173.75 | 5 |  | SCM - 2023.R6 08/23
WMSP-8434 | High | Senaida Bradtke | Request - Paused | New Feature |  | 208.75 | 1 |  | SCM - 2023.R1 00/23
WMSP-0317 | Urgent | Art Leannon | External Dependency | Architectural | 8 | 405 | 8 |  | SCM - 2023.R3 09/23
WMSP-1535 | Normal | Adah Stanton | Coding Queue | Architectural | 13 | 223.75 | 8 |  | SCM - 2023.R9 05/23
WMSP-8554 | Low | Elijah Berge | Coding Review Queue | Architectural | 21 | 208.75 | 5 | 4 | SCM - 2023.R8 04/23
WMSP-8157 | High | Truman Hackett | Request - Paused | Defect |  | 138.75 | 0 |  | SCM - 2023.R9 05/23
WMSP-3138 | Lowest | Catharine Wehner | Coding Queue | Defect |  | 348.75 | 8 |  | SCM - 2023.R1 04/23
WMSP-9095 | Low | Cody Stehr | Coding Review Queue | New Feature | 2 | 238.75 | 13 |  | SCM - 2023.R9 07/23
WMSP-8256 | Lowest | Bertie Stiedemann | Coding Review Queue | New Feature | 3 | 183.75 | 3 |  | SCM - 2023.R5 05/23
WMSP-9006 | Lowest | Elvin Reynolds | Coding | Architectural | 5 | 158.75 | 5 |  | SCM - 2023.R8 05/23
WMSP-7939 | Normal | Cameron Jerde | Coding Queue | Architectural | 3 | 0 |  |  | SCM - 2023.R3 09/23
WMSP-7453 | Lowest | Marco Witting | Coding Queue | Architectural | 8 | 173.75 | 0 |  | SCM - 2023.R5 08/23
WMSP-7299 | Low | Wilma Lockman | Coding Queue | New Feature | 13 | 316.25 | 0 |  | SCM - 2023.R7 09/23
WMSP-2284 | Lowest | Ruthann Russel | External Dependency | Defect | 21 | 108.75 | 13 |  | SCM - 2023.R7 05/23
WMSP-0472 | Normal | Otto Schowalter | External Dependency | Architectural | 0 | 405 | 1 |  | SCM - 2023.R6 08/23
WMSP-1366 | Normal | Mohammed Kutch | Request - Paused | Defect | 1 | 208.75 | 13 |  | SCM - 2023.R7 03/23
WMSP-3439 | Lowest | Mario Aimonetti | Coding Review Queue | Defect | 2 | 103.75 | 13 |  | SCM - 2023.R1 00/23
WMSP-5105 | Urgent | Gregg McDermott | Request - Paused | Architectural | 3 | 223.75 | 2 |  | SCM - 2023.R0 08/23
WMSP-7214 | Lowest | Chance Leannon | Coding Queue | Architectural | 5 | 301.25 | 3 |  | SCM - 2023.R5 08/23
WMSP-8715 | Normal | Jarod Hickle | External Dependency | New Feature | 3 | 316.25 | 5 |  | SCM - 2023.R6 01/23
WMSP-3238 | Low | Gavin Pagac | Coding Review Queue | Defect | 8 | 208.75 | 1 |  | SCM - 2023.R0 00/23
WMSP-4158 | High | Tracey Wisozk | Request - Paused | New Feature | 13 | 301.25 | 1 | 9 | SCM - 2023.R9 00/23
WMSP-3224 | Normal | Syble Huel | External Dependency | Architectural | 21 | 353.75 | 1 |  | SCM - 2023.R9 07/23
WMSP-4678 | Lowest | Josefine Runolfsson | External Dependency | New Feature | 0 | 173.75 | 13 |  | SCM - 2023.R2 08/23
WMSP-8892 | Urgent | Anibal Mitchell | External Dependency | New Feature | 1 | 183.75 | 2 |  | SCM - 2023.R0 04/23
WMSP-3039 | Normal | Donette Langosh | Coding Review Queue | Architectural | 2 | 223.75 | 1 |  | SCM - 2023.R9 02/23
WMSP-6155 | High | Zelma Yost | Request - Paused | Defect | 3 | 238.75 | 1 |  | SCM - 2023.R7 08/23
WMSP-1119 | High | Oralia Rolfson | Request - Paused | New Feature | 5 | 353.75 | 2 |  | SCM - 2023.R4 03/23
WMSP-3771 | Low | Delcie Farrell | Coding | Defect | 3 | 405 | 1 |  | SCM - 2023.R7 08/23
WMSP-1902 | Normal | Clifford Jenkins | Coding Queue | New Feature | 8 | 238.75 | 1 |  | SCM - 2023.R7 08/23
WMSP-5129 | Low | Alvera Greenfelder | Coding Review Queue | Architectural | 13 | 238.75 | 5 |  | SCM - 2023.R0 01/23
WMSP-6076 | High | Gayle Von | Coding | Architectural | 21 | 348.75 | 0 |  | SCM - 2023.R1 03/23
WMSP-7043 | Lowest | Arlie Bernier | Coding | Architectural | 0 | 173.75 | 1 |  | SCM - 2023.R0 01/23

## Data7
Key | Priority | Assignee | Status | Request Type | Story Points (Coding) | Business Value | Story Points (Test) | Planned Logo Week | Sprint
WMSP-9135 | High | Jonas Emmerich | External Dependency | Architectural | 13 | 313.75 | 5 |  | SCM - 2023.R7 00/23
WMSP-4071 | Normal | Lindy Cronin | Coding | Architectural | 1 | 103.75 | 1 |  | SCM - 2023.R8 02/23
WMSP-9458 | Urgent | Oretha Tillman | Request - Paused | New Feature | 0 | 353.75 | 5 |  | SCM - 2023.R0 04/23
WMSP-9829 | Lowest | Josefine Cremin | Coding Queue | New Feature | 3 | 208.75 | 1 |  | SCM - 2023.R3 02/23
WMSP-6445 | Urgent | Buford Kemmer | Coding Queue | Architectural | 8 | 288.75 | 1 |  | SCM - 2023.R8 04/23
WMSP-9428 | Urgent | Maegan O'Keefe | Request - Paused | New Feature | 2 | 313.75 | 1 |  | SCM - 2023.R2 01/23
WMSP-4298 | High | Robin Quitzon | Coding Review Queue | Architectural | 3 | 218.75 | 1 |  | SCM - 2023.R7 05/23
WMSP-9743 | High | Floyd White | Coding | Defect | 5 | 138.75 | 1 |  | SCM - 2023.R8 04/23
WMSP-1527 | High | Rico Kunze | External Dependency | Architectural | 2 | 183.75 | 0 |  | SCM - 2023.R3 00/23
WMSP-6734 | Urgent | Zack Legros | Coding Review Queue | New Feature | 2 | 288.75 | 13 |  | SCM - 2023.R5 07/23
WMSP-6372 | Normal | Sonya Gutmann | Coding Review Queue | Architectural | 21 | 313.75 | 8 |  | SCM - 2023.R4 06/23
WMSP-1790 | Normal | Christel Berge | Coding | New Feature | 1 | 138.75 | 1 |  | SCM - 2023.R7 05/23
WMSP-8222 | Low | Jesica Lesch | Coding | Architectural | 34 | 0 | 1 |  | SCM - 2023.R3 04/23
WMSP-1295 | Urgent | Syble Hickle | External Dependency | New Feature | 34 | 313.75 | 1 |  | SCM - 2023.R4 05/23
WMSP-8493 | High | Bradley Brown | Coding | New Feature | 21 | 173.75 | 13 |  | SCM - 2023.R2 05/23
WMSP-9517 | Normal | Kyle Mills | Coding | New Feature | 3 | 173.75 | 2 |  | SCM - 2023.R5 02/23
WMSP-7411 | Low | Andre Romaguera | Request - Paused | Defect | 3 | 353.75 | 1 |  | SCM - 2023.R7 02/23
WMSP-8715 | Urgent | Alonzo Hodkiewicz | External Dependency | Defect | 3 | 238.75 | 13 |  | SCM - 2023.R9 02/23
WMSP-5065 | Urgent | Donald Harber | Request - Paused | Defect | 3 | 173.75 | 8 |  | SCM - 2023.R9 00/23
WMSP-7165 | High | Chadwick Koss | Request - Paused | Defect | 3 | 108.75 | 1 |  | SCM - 2023.R2 07/23
WMSP-3277 | Lowest | Frederic Weimann | Coding | Defect | 3 | 208.75 | 1 |  | SCM - 2023.R4 07/23
WMSP-4025 | Normal | Philip Weissnat | Coding Queue | Architectural | 8 | 288.75 | 3 |  | SCM - 2023.R6 06/23
WMSP-7932 | High | Santiago Bins | Coding | New Feature | 0 | 138.75 | 0 |  | SCM - 2023.R2 00/23
WMSP-1392 | Lowest | Raymond Batz | Coding Queue | Architectural | 5 | 188.75 | 1 |  | SCM - 2023.R0 02/23
WMSP-6876 | Lowest | Dewayne Wiza | Coding Queue | Architectural | 0 | 0 | 3 | 4 | SCM - 2023.R9 03/23
WMSP-1199 | Normal | Bernard Hackett | Request - Paused | Defect | 5 | 108.75 | 13 |  | SCM - 2023.R9 09/23
WMSP-6802 | Urgent | Miquel Pollich | Coding Queue | Defect | 5 | 353.75 | 3 |  | SCM - 2023.R3 04/23
WMSP-2588 | Urgent | Deandre Durgan | Coding Queue | Architectural | 3 | 0 | 8 |  | SCM - 2023.R4 03/23
WMSP-4883 | Urgent | Sanford Bernier | Request - Paused | Architectural | 0 | 405 | 13 |  | SCM - 2023.R8 09/23
WMSP-6347 | Low | Eladia Thiel | Coding Queue | New Feature | 2 | 103.75 | 0 |  | SCM - 2023.R4 09/23

## FrequencyRate
# | Selected Issue Type | Defect.Normal.300.8.0 | Defect.Normal.200.3.3 | Defect.High.300.3.3 | Defect.High.300.8.3 | New Feature.Normal.300.3.3 | New Feature.Normal.300.3.8 | New Feature.Normal.300.8.3 | New Feature.Normal.200.0.3 | New Feature.Normal.200.0.8 | New Feature.Normal.200.3.3 | New Feature.Normal.200.8.3 | New Feature.Normal.200.13.8 | New Feature.Normal.258.75.0.3 | New Feature.High.300.1.1 | New Feature.High.300.3.3 | New Feature.High.200.3.8
1 | New Feature.Normal.300.3.3 | 2 | 3 | 3 | 2 | 5 | 4 | 4 | 3 | 2 | 4 | 3 | 2 | 3 | 2 | 4 | 2 | WMSP-8681
2 | New Feature.Normal.200.8.3 | 2 | 3 | 1 | 2 | 3 | 2 | 4 | 4 | 3 | 4 | 5 | 3 | 3 | 1 | 2 | 2 | WMSP-7328
3 | New Feature.High.200.3.8 | 0 | 2 | 2 | 1 | 2 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 5 | WMSP-8499
4 | Defect.Normal.300.8.0 | 5 | 2 | 2 | 3 | 2 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | WMSP-8206
5 | New Feature.Normal.200.3.3 | 1 | 4 | 2 | 1 | 4 | 3 | 3 | 4 | 3 | 5 | 4 | 3 | 3 | 1 | 3 | 3 | WMSP-8594
6 | New Feature.High.300.3.3 | 1 | 2 | 4 | 3 | 4 | 3 | 3 | 2 | 1 | 3 | 2 | 1 | 2 | 3 | 5 | 3 | WMSP-8574
7 | New Feature.Normal.200.13.8 | 1 | 2 | 0 | 0 | 2 | 3 | 2 | 3 | 4 | 3 | 3 | 5 | 2 | 1 | 1 | 3 | WMSP-7958
8 | New Feature.Normal.300.8.3 | 3 | 2 | 2 | 3 | 4 | 3 | 5 | 3 | 2 | 3 | 4 | 2 | 3 | 2 | 3 | 1 | WMSP-8674
9 | Defect.Normal.200.3.3 | 2 | 5 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 4 | 3 | 2 | 2 | 0 | 2 | 2 | WMSP-8549
10 | New Feature.High.300.1.1 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 3 | 2 | WMSP-8644
11 | New Feature.Normal.258.75.0.3 | 1 | 2 | 1 | 1 | 3 | 2 | 3 | 4 | 3 | 3 | 3 | 2 | 5 | 1 | 2 | 1 | WMSP-8833
12 | New Feature.Normal.200.3.3 | 1 | 4 | 2 | 1 | 4 | 3 | 3 | 4 | 3 | 5 | 4 | 3 | 3 | 1 | 3 | 3 | WMSP-8573
13 | Defect.High.300.8.3 | 3 | 2 | 4 | 5 | 2 | 1 | 3 | 1 | 0 | 1 | 2 | 0 | 1 | 2 | 3 | 1 | WMSP-8473
14 | New Feature.Normal.300.3.8 | 2 | 2 | 2 | 1 | 4 | 5 | 3 | 2 | 3 | 3 | 2 | 3 | 2 | 2 | 3 | 3 | WMSP-8683
15 | New Feature.Normal.200.3.3 | 1 | 4 | 2 | 1 | 4 | 3 | 3 | 4 | 3 | 5 | 4 | 3 | 3 | 1 | 3 | 3 | WMSP-8542
16 | New Feature.Normal.300.8.3 | 3 | 2 | 2 | 3 | 4 | 3 | 5 | 3 | 2 | 3 | 4 | 2 | 3 | 2 | 3 | 1 | WMSP-8673
17 | Defect.High.300.3.3 | 2 | 3 | 5 | 4 | 3 | 2 | 2 | 1 | 0 | 2 | 1 | 0 | 1 | 2 | 4 | 2 | WMSP-8599
18 | New Feature.Normal.200.0.8 | 1 | 2 | 0 | 0 | 2 | 3 | 2 | 4 | 5 | 3 | 3 | 4 | 3 | 1 | 1 | 3 | WMSP-8616
19 | New Feature.Normal.200.0.3 | 1 | 3 | 1 | 1 | 3 | 2 | 3 | 5 | 4 | 4 | 4 | 3 | 4 | 1 | 2 | 2 | WMSP-8834

## IssueWeekSheet
# | Selected Issue Type | Key | Week | Business Value | Priority | Request Type | Story Points (Coding) | Story Points (Test) |  | Sum of Weeks' Story Point (Coding) Values | Issue Counts Per Week
1 | New Feature.Low.200.C.C | WMSP-4015 | 1 | 200 | Low | New Feature | C | C | 1 | 342 | 31
2 | New Feature.High.300.A.G | WMSP-6579 | 1 | 300 | High | New Feature | G | A | 2 | 336 | 33
3 | Defect.Normal.400.F.F | WMSP-3451 | 1 | 400 | Normal | Defect | F | F | 3 | 334 | 36
4 | New Feature.Low.200.B.A | WMSP-5049 | 1 | 200 | Low | New Feature | A | B
5 | New Feature.High.100.A.H | WMSP-3055 | 1 | 100 | High | New Feature | H | A | ** Divided by 2 Sprints
6 | Defect.Low.200.C.D | WMSP-7108 | 1 | 200 | Low | Defect | D | C
7 | New Feature.Normal.200.E.C | WMSP-2319 | 1 | 200 | Normal | New Feature | C | E
8 | New Feature.High.300.C.A | WMSP-2000 | 1 | 300 | High | New Feature | - | C
9 | Defect.Low.200.D.H | WMSP-5465 | 1 | 200 | Low | Defect | H | D
10 | New Feature.High.100.A.E | WMSP-3553 | 1 | 100 | High | New Feature | E | A
11 | New Feature.Normal.200.F.C | WMSP-7691 | 1 | 200 | Normal | New Feature | C | F
12 | New Feature.Low.300.E.D | WMSP-9337 | 1 | 300 | Low | New Feature | D | E
13 | Defect.Low.200.C.F | WMSP-1269 | 1 | 200 | Low | Defect | F | C
14 | New Feature.High.400.A.A | WMSP-8192 | 1 | 400 | High | New Feature | - | A
15 | New Feature.Normal.200.B.G | WMSP-7435 | 1 | 200 | Normal | New Feature | G | B
16 | Defect.High.0.A.C | WMSP-1657 | 1 | 0 | High | Defect | C | A
17 | New Feature.Low.200.C.H | WMSP-2811 | 1 | 200 | Low | New Feature | H | C
18 | New Feature.High.300.C.B | WMSP-3911 | 1 | 300 | High | New Feature | B | C
19 | New Feature.Low.200.E.E | WMSP-3912 | 1 | 200 | Low | New Feature | E | E
20 | Defect.Normal.100.A.C | WMSP-0238 | 1 | 100 | Normal | Defect | C | A
21 | New Feature.Low.200.F.A | WMSP-8750 | 1 | 200 | Low | New Feature | A | F
22 | New Feature.High.400.C.G | WMSP-8862 | 1 | 400 | High | New Feature | G | C
23 | New Feature.Low.200.D.F | WMSP-4528 | 1 | 200 | Low | New Feature | F | D
24 | Defect.Normal.300.A.C | WMSP-4060 | 1 | 300 | Normal | Defect | C | A
25 | New Feature.High.200.C.H | WMSP-8337 | 1 | 200 | High | New Feature | H | C
26 | New Feature.Low.300.B.A | WMSP-2780 | 1 | 300 | Low | New Feature | A | B
27 | Defect.Low.200.A.D | WMSP-7024 | 1 | 200 | Low | Defect | D | A
28 | New Feature.High.200.E.C | WMSP-0263 | 1 | 200 | High | New Feature | C | E
29 | New Feature.Normal.100.C.F | WMSP-6388 | 1 | 100 | Normal | New Feature | F | C
30 | Defect.Low.400.A.H | WMSP-0784 | 1 | 400 | Low | Defect | H | A
31 | New Feature.High.200.F.C | WMSP-9911 | 1 | 200 | High | New Feature | C | F
32 | New Feature.High.300.E.A | WMSP-3286 | 2 | 300 | High | New Feature | A | E
33 | New Feature.Normal.200.A.B | WMSP-3541 | 2 | 200 | Normal | New Feature | B | A
34 | Defect.Low.100.C.C | WMSP-8238 | 2 | 100 | Low | Defect | C | C
66 | New Feature.Low.300.D.A | WMSP-7660 | 2 | 300 | Low | New Feature | A | D
36 | New Feature.Low.300.C.G | WMSP-9244 | 2 | 300 | Low | New Feature | G | C
37 | New Feature.Low.200.E.E | WMSP-6823 | 2 | 200 | Low | New Feature | E | E
38 | New Feature.Normal.200.F.A | WMSP-3564 | 2 | 200 | Normal | New Feature | A | F
39 | Defect.High.400.B.H | WMSP-4938 | 2 | 400 | High | Defect | H | B
40 | New Feature.Low.200.A.A | WMSP-2712 | 2 | 200 | Low | New Feature | - | A
41 | New Feature.Normal.300.C.C | WMSP-8378 | 2 | 300 | Normal | New Feature | C | C
42 | Defect.Low.100.A.G | WMSP-1058 | 2 | 100 | Low | Defect | G | A
43 | New Feature.High.200.C.F | WMSP-7212 | 2 | 200 | High | New Feature | F | C
44 | New Feature.Low.0.F.H | WMSP-8834 | 2 | 0 | Low | New Feature | H | F
45 | Defect.High.200.A.C | WMSP-9640 | 2 | 200 | High | Defect | C | A
46 | New Feature.Normal.400.B.D |  | 2 | 400 | Normal | New Feature | D | B
47 | New Feature.Low.200.E.F | WMSP-3706 | 2 | 200 | Low | New Feature | F | E
48 | New Feature.High.300.C.A | WMSP-1752 | 2 | 300 | High | New Feature | A | C
49 | Defect.Low.200.A.C | WMSP-1932 | 2 | 200 | Low | Defect | C | A
50 | New Feature.High.100.C.E | WMSP-0658 | 2 | 100 | High | New Feature | E | C
51 | New Feature.Normal.200.E.G | WMSP-3002 | 2 | 200 | Normal | New Feature | G | E
52 | Defect.Low.200.A.D | WMSP-1386 | 2 | 200 | Low | Defect | D | A
53 | New Feature.Low.400.D.H | WMSP-1006 | 2 | 400 | Low | New Feature | H | D
54 | New Feature.High.300.C.C | WMSP-7337 | 2 | 300 | High | New Feature | C | C
55 | New Feature.High.200.A.B | WMSP-9816 | 2 | 200 | High | New Feature | B | A
56 | New Feature.Normal.300.F.A | WMSP-8140 | 2 | 300 | Normal | New Feature | A | F
57 | Defect.Low.200.C.C | WMSP-8391 | 2 | 200 | Low | Defect | C | C
58 | New Feature.High.200.A.F | WMSP-8788 | 2 | 200 | High | New Feature | F | A
59 | New Feature.Low.100.E.E | WMSP-5075 | 2 | 100 | Low | New Feature | E | E
60 | Defect.Normal.200.B.C | WMSP-8111 | 2 | 200 | Normal | Defect | C | B
61 | New Feature.Low.400.C.A | WMSP-4536 | 2 | 400 | Low | New Feature | A | C
62 | New Feature.High.200.A.H | WMSP-2927 | 2 | 200 | High | New Feature | H | A
63 | Defect.Normal.100.C.D | WMSP-1471 | 2 | 100 | Normal | Defect | D | C
64 | New Feature.Low.300.F.H | WMSP-4606 | 2 | 300 | Low | New Feature | H | F
65 | New Feature.High.200.E.G | WMSP-8161 | 3 | 200 | High | New Feature | G | E
35 | New Feature.High.200.D.D | WMSP-9505 | 3 | 200 | High | New Feature | D | D
67 | Defect.Normal.0.A.C | WMSP-6073 | 3 | 0 | Normal | Defect | C | A
68 | New Feature.Low.200.F.F | WMSP-6824 | 3 | 200 | Low | New Feature | F | F
69 | New Feature.High.200.C.A | WMSP-9575 | 3 | 200 | High | New Feature | A | C
70 | New Feature.High.200.A.D | WMSP-7490 | 3 | 200 | High | New Feature | D | A
71 | Defect.Low.200.B.F | WMSP-1986 | 3 | 200 | Low | Defect | F | B
72 | New Feature.Low.300.C.C | WMSP-3279 | 3 | 300 | Low | New Feature | C | C
73 | New Feature.Normal.400.A.E | WMSP-4347 | 3 | 400 | Normal | New Feature | E | A
74 | New Feature.High.200.C.H | WMSP-7556 | 3 | 200 | High | New Feature | H | C
75 | Defect.Normal.200.A.G | WMSP-9207 | 3 | 200 | Normal | Defect | G | A
76 | New Feature.Low.400.D.C | WMSP-1110 | 3 | 400 | Low | New Feature | C | D
77 | New Feature.High.100.C.A | WMSP-3164 | 3 | 100 | High | New Feature | - | C
78 | Defect.Low.300.E.H | WMSP-9609 | 3 | 300 | Low | Defect | H | E
79 | New Feature.High.200.F.C | WMSP-7732 | 3 | 200 | High | New Feature | C | F
80 | Defect.Low.200.A.B | WMSP-8480 | 3 | 200 | Low | Defect | B | A
81 | New Feature.Normal.200.E.F | WMSP-1300 | 3 | 200 | Normal | New Feature | F | E
82 | New Feature.High.100.A.A | WMSP-3440 | 3 | 100 | High | New Feature | A | A
83 | New Feature.Low.200.C.C | WMSP-5464 | 3 | 200 | Low | New Feature | C | C
84 | New Feature.High.300.E.D | WMSP-5600 | 3 | 300 | High | New Feature | D | E
85 | Defect.Low.200.B.A | WMSP-5607 | 3 | 200 | Low | Defect | A | B
86 | New Feature.Normal.0.A.E | WMSP-8083 | 3 | 0 | Normal | New Feature | E | -
87 | New Feature.High.200.F.G | WMSP-0525 | 3 | 200 | High | New Feature | G | F
88 | New Feature.Low.300.C.F | WMSP-5014 | 3 | 300 | Low | New Feature | F | C
89 | Defect.Low.400.C.A | WMSP-6125 | 3 | 400 | Low | Defect | A | C
90 | New Feature.High.200.A.H | WMSP-9166 | 3 | 200 | High | New Feature | H | A
91 | New Feature.Normal.100.F.C | WMSP-7341 | 3 | 100 | Normal | New Feature | C | F
92 | New Feature.High.200.B.G | WMSP-3173 | 3 | 200 | High | New Feature | G | B
93 | Defect.Normal.300.E.D | WMSP-5503 | 3 | 300 | Normal | Defect | D | E
94 | New Feature.Low.200.A.H | WMSP-3317 | 3 | 200 | Low | New Feature | H | A
95 | Defect.Low.200.C.A | WMSP-4177 | 3 | 200 | Low | Defect | A | C
96 | New Feature.Low.400.A.C | WMSP-7425 | 3 | 400 | Low | New Feature | C | A
97 | New Feature.High.200.C.A | WMSP-2961 | 3 | 200 | High | New Feature | A | C
98 | Defect.High.300.A.C | WMSP-5869 | 3 | 300 | High | Defect | C | A
99 | New Feature.Normal.100.D.A | WMSP-4509 | 3 | 100 | Normal | New Feature | A | D
100 | New Feature.Low.200.C.A | WMSP-0292 | 3 | 200 | Low | New Feature | A | C